## Sheet1
Sprint | Project total points | Completed | Cumulative completed | estimated trajectory
0 | 180 | 0 | 0 | 0
1 | 180 | 50 | 50 | #N/A
2 | 180 | 90 | 140 | #N/A
3 | 180 | 30 | 170 | 180
Sprint1:
Work completed:
Basic layout for the website. 10
User login and signup. 10
Be able to upload the pictures. 10
Be able to comment for each picture 10
Be able to delete the pictures and information 10
Work not completed 10
Create web profile for every new user. 10
Let user add information on their profile(name,tel,hobby). 10
Sprint1 total completed: 50/80
Sprint2:
Work completed:
Be able to Sort the pictures by time 10
Add comment to the picture. 10
Finished user profile. 10
Now you can follow people you like. 10
Finished artist page which you will see all of artists with their pictures. 10
Not completed:
List all of the pictures of following people. 10
Thumb up function. 10
Sprint2 total completed: 50/70
Sprint3:
Work completed:
Search function 10
Like function. 10
Not completed:
Login with google account is not completed. 10
Sprint3 total completed: 20/30